## Action Tracker
The Vintage at Hamilton HOA — Board Action Tracker
Updated: June 11, 2026
ID | Category | Item / Action | Detail | Owner | Due / Target | Status | Notes / Update
1 | Gym Relocation | Move gym to new building | Investigate relocating existing gym equipment into one of the two proposed rooms in the new building | Board / RCP | 7/7/2026 | Open | Approved for investigation 6/10
2 | Gym Relocation | Second room usage | Usage TBD. Options under investigation: (a) movable wall between the two rooms; (b) general use with expanded fitness options (yoga, etc.) | Board | 7/7/2026 | Open | Decision deferred pending options
3 | Clubhouse Expansion | Replace wall between clubhouse and existing gym | Options: removable/movable wall, or large French doors — to open existing gym space for expanded clubhouse activities | Board / RCP | 7/7/2026 | Open | Approved for investigation 6/10
4 | Storage | Storage solution — build vs. shed | Either build an outside storage facility or purchase/install freestanding shed(s) for outdoor furniture (winter), surplus indoor furniture, and social committee items | RCP / Sharbell | 7/7/2026 | Open | RCP to work with Sharbell; full estimates and options due 7/7
5 | Storage | Location option A — dumpster area | Utilize 2–3 parking spaces alongside existing dumpster location in clubhouse carpark | RCP / Sharbell | 7/7/2026 | Open | Scope and estimate requested
6 | Storage | Location option B — Stone Terrace fence line | Utilize space over the fence between the development and the Stone Terrace carpark. Verify HOA owns 10 ft beyond fence | RCP / Sharbell | 7/7/2026 | Open | Ownership of 10 ft strip to be confirmed
7 | Storage | Location option C — behind 85 Kay Chiarello Way | Utilize common area behind 85 Kay Chiarello Way (and potentially adjacent properties), incorporating existing gate in fence | RCP / Sharbell | 7/7/2026 | Open | May need inclement-weather/mud mitigation
8 | Meetings | Request first official board meeting | Email Al Pellegrino (apellegrino@rcpmanagement.com) to set up first official board meeting — 7/7/2026, 6:30 PM, clubhouse | Keith | ASAP | Open
9 | Meetings | Resident members follow-up meeting | 7/2/2026, 6:30 PM at clubhouse — finalize proposed agenda for first official board meeting | All resident members | 7/2/2026 | Scheduled
10 | Governance | Confirm committees and membership | Confirmation of committees and their membership | Board | 7/7/2026 | Open | Agenda item for 7/7
11 | Governance | Committee representation at board meetings | Agree how committees are represented at board meetings | Board | 7/7/2026 | Open | Agenda item for 7/7
12 | Governance | Active contracts review | Understand contracts currently active, renewal requirements, and timelines | Board / RCP | 7/7/2026 | Open | Agenda item for 7/7
13 | Governance | Board members roles & responsibilities | Confirm board member R&R | Board | 7/7/2026 | Open | Agenda item for 7/7
14 | Finance | Social committee funding | Funding discussion for social committee | Board | 7/7/2026 | Open | Agenda item for 7/7
15 | Finance | Reserve fund | Requirements to fund a reserve fund for emergency use (e.g., road repairs) | Board | 7/7/2026 | Open | Agenda item for 7/7
16 | Finance | Budget & actuals review process | Ability to review budget and financial actuals on a regular schedule, tied in with Finance committee | Board / Finance Cmte | 7/7/2026 | Open | Agenda item for 7/7
Summary
Open
In Progress
Scheduled
Blocked
Complete
Total items

## Contacts
Resident Board Members — Contacts
Name | Address | Phone | Email | Role(s)
Keith Dyke | 24 Kay Chiarello Way | 609-613-6452 | keith_dyke@hotmail.com | HOA Board Member; Web Master
Sudhir Kalra | 9 Sportsman Boulevard | 917-865-9397 | skalra@optonline.net | HOA Board Member
Bill Linder | 2 Isabella Court | 609-610-4977 | wtlsr@aol.com | HOA Board Member
Wally Sawka | 10 Isabella Court | 609-947-0176 | wsawka@me.com | HOA Board Member
Al Pellegrino (RCP Management) |  |  | apellegrino@rcpmanagement.com | Property Manager